## Sprint Backlog
| SPRINT 3 BACKLOG | [5 empty] | *(1) All tasks assume a boilerplate project starting point (2) All completed features require tests (3) Backend routes should be documented
ID | ITEM | OWNER | PRIORITY | POINTS | STATUS | SPRINT | TASKS*
43 | As a customer I want to be able to leave a review for a specific shop owner/vendor that I have purchased a book from so I can inform other users of the quality of service | Thomas | High | 3 | Done | Sprint 3 | (Frontend) Create profile details page, Create ProfileReviewList component, Create a profile review form (Backend) Create ProfileReview JPA entity and repo, Create UserProfiles Controller, Create GET UserProfileReviews route
19 | As a customer I want to be able to leave a review on a specific book that has been posted to Bookaroo so I can help other users know if the book is worthy of purchase | Thomas | High | 3 | Done | Sprint 3 | (Frontend) Create book details page, Create BookReviewList component, Create BookReviewForm component (Backend) Create BookReview JPA entity and repo, Create GET Reviews route under BookController
40 | As a customer I want to be able to leave a rating for a book that is listed on Bookaroo so I can provide feedback that other users can view | Thomas | High | 3 | Done | Sprint 3 | (Frontend) Create book details page, Create BookReviewList component, Create BookReviewForm component (Backend) Create BookReview JPA entity and repo, Create GET Reviews route under BookController
21 | As a customer I want to be able to complete a purchase of a book via PayPal so I can ensure my payment was done securely | Thomas | High | 3 | Done | Sprint 3 | (Frontend) Create AddToCartButton component, Create checkout page, Create checkout form (Backend) Create TransactionItem JPA entity and repo, Create Transactions Controller, Create POST route for completing a transaction that coordinates with the PayPal API
24 | As a customer I want to be able to view a history of my transactions so I can keep track of what I have bought | Sefanur | Medium | 3 | Done | Sprint 3 | (Frontend) Create "my orders" page, Create OrderList component (Backend) Create Transaction JPA entity and repo, Create Transactions Controller, Create Transactions GET route
25 | As a shop owner I want to be able to view the transaction history of my shop so I can track my orders and ensure they are all fulfilled | Sefanur | Medium | 3 | Done | Sprint 3 | (Frontend) Create "my orders" page, Create OrderList component, Add "cancel" button to orders (Backend) Create Transaction JPA entity and repo, Create Transactions Controller, Create Transactions GET route
45 | As a customer I want to be able to view the current status of my order so I can keep up to date with when I will receive my order |  | Medium | 2 | Cancelled | Sprint 3 | (Frontend) Create "my orders" page, Create OrderList component (Backend) Create Transaction JPA entity and repo, Create Transactions Controller, Create Transactions GET route
44 | As a customer I want to be able to leave a review on another customers profile so I can help any other customers that may interact with this profile to be aware of the customers service history | Thomas | Medium | 3 | Done | Sprint 3 | (Frontend) Create profile details page, Create ProfileReviewList component, Create a profile review form (Backend) Create ProfileReview JPA entity and repo, Create UserProfiles Controller, Create GET UserProfileReviews route
46 | As a shop owner I want to be able to update the status of an order made to me so I can keep the customer up to date with their order |  | Low | 5 | Cancelled | Sprint 3 | (Frontend) Create "my orders" page, Create OrderList component, Create "update status" control (Backend) Create Transaction JPA entity and repo, Create Transactions Controller, Create Transactions GET route, Create Transactions POST update status route
48 | As a customer I want to be able to update the status of a order made for one of the used books I am selling so I can show the buyer the progress of their order |  | Low | 5 | Cancelled | Sprint 3 | (Frontend) Create "my orders" page, Create OrderList component, Create "update status" control (Backend) Create Transaction JPA entity and repo, Create Transactions Controller, Create Transactions GET route, Create Transactions POST update status route
28 | As an admin user I want to be able to download a report of all transactions within a given time period so I can track user engagement and site popularity |  | Low | 2 | Cancelled | Sprint 3 | (Frontend) Create a DownloadTransactionsButton component, Add a DownloadTransactionsButton to the admin dashboard page (Backend) Create a Transaction GET all route
22 | As a customer I want to be able to cancel an order up to 2 hours after I place the order in case so I can change my mind on purchases I make | Ewan | Low | 2 | Done | Sprint 3 | (Frontend) Create "my orders" page, Create OrderList component, Add "cancel" button to orders that occurred within the last 2 hours (Backend) Add a CancelTransaction POST route to Transactions Controller
13 | As an admin user I want to be able to view a summary of all transactions on the site sorted by date to verify details of purchases that have been made | Sefanur | Low | 3 | Done | Sprint 3 | (Frontend) Create admin transactions page, Create TransactionList component (Backend) Create Transaction JPA entity and repo, Create Transaction Controller, Create Transaction GET route

## TasksForJiraExport
Task
Setup AWS Amplify
Create login page
Create login form Setup user pools on AWS Cognito
write middleware for decoding and verifying the Cognito JWT
guard relevant routes
Setup AWS Amplify
Create login page
Create login form Setup user pools on AWS Cognito
write middleware for decoding and verifying the Cognito JWT
guard relevant routes
Setup AWS Amplify
Create login page
Create login form Setup user pools on AWS Cognito
write middleware for decoding and verifying the Cognito JWT
guard relevant routes
Add a 'logout' button to the navigation bar
Add a 'logout' button to the navigation bar
Add a 'logout' button to the navigation bar
Setup AWS Amplify
Create standard signup page
Create standard signup form
Setup AWS Amplify
Create shop owner signup page
Create shop owner signup formCreate ShopOwnerApplication POST route on User controller
Create admin shop owner application page
Create ShopOwnerApplicationList componentCreate ShopOwnerApplication JPA entity and repo
Create ShopOwnerApplication Controller
Create ShopOwnerApplication GET route
Create admin user list page
Create UserList component
Create form for updating usersCreate UserEntity JPA entity and repo
Create UserProfile controller
Create UserProfile PATCH Route
Create admin user list page
Create UserList component
Create action button for suspending usersCreate UserProfile JPA entity and repo
Create UserProfile controller
Create UserProfile Suspend PATCH route
Create admin shop owner application page
Create ShopOwnerApplicationList componentCreate ShopOwnerApplication JPA entity and repo
Create ShopOwnerApplication Controller
Create ShopOwnerApplication GET route
Create admin transactions page
Create TransactionList componentCreate Transaction JPA entity and repo
Create Transaction Controller
Create Transaction GET route
Create admin user list page
Create UserList component
Create action button for unsuspending usersCreate UserProfile JPA entity and repo
Create UserProfile controller
Create UserProfile Suspend PATCH route
Create Book component
Create BookGrid component
Create FilteredBookGrid component
Create books pageCreate Book JPA entity and repo
Create Book controller
Create Filtered GET Book Route
Create Book component
Create BookGrid component
Create FilteredBookGrid component
Create books pageCreate Book JPA entity and repo
Create Book controller
Create Filtered GET Book Route
Create Book component
Create BookGrid component
Create FilteredBookGrid component
Create books pageCreate Book JPA entity and repo
Create Book controller
Create Filtered GET Book Route
Create Book component
Create BookGrid component
Create FilteredBookGrid component
Create books pageCreate Book JPA entity and repo
Create Book controller
Create Filtered GET Book Route
Create book details page
Create BookReviewList component
Create BookReviewForm componentCreate BookReview JPA entity and repo
Create GET Reviews route under BookController
Create BookListingsList component
Add listings to book details page Create BookListing JPA entity and repo
Create BookListings Controller
Create GET BookListings Route
Create AddToCartButton component
Create checkout page
Create checkout formCreate TransactionItem JPA entity and repo
Create Transactions Controller
Create POST route for completing a transaction that coordinates with the PayPal API
Create 'my orders' page
Create OrderList component
Add 'cancel' button to orders that occurred within the last 2 hoursAdd a CancelTransaction POST route to Transactions Controller
Add a 'swap' option to the create listing form
Update BookListing component for 'swap' listingsAdd a listingType field to the BookListing JPA entity
Create 'my orders' page
Create OrderList component
Add 'cancel' button to ordersCreate Transaction JPA entity and repo
Create Transactions Controller
Create Transactions GET route
Create 'my orders' page
Create OrderList component
Add 'cancel' button to ordersCreate Transaction JPA entity and repo
Create Transactions Controller
Create Transactions GET route
Create book detail pageCreate Book JPA entity and repo
Create Books controller
Create GET Book route
Create a DownloadBookListingsButton component
Add a DownloadBookListingsButton to the admin dashboard pageCreate a BookListing GET all route
Create a DownloadTransactionsButton component
Add a DownloadTransactionsButton to the admin dashboard pageCreate a Transaction GET all route
Create a 'contact' page
Create a 'contact' page
Create an 'about' page
Create an 'about' page
Add a 'list a new book' nav bar item
Add a 'list new book' action button to the home page
Create a 'create listing' page
Create the 'create listing' form
Create 'create book details' form
Implement pre-filling book fields from openlibrary APICreate a POST BookListing Route
Create a POST Book Route
Add a 'list a new book' nav bar item
Add a 'list new book' action button to the home page
Create a 'create listing' page
Create the 'create listing' form
Create 'create book details' form
Implement pre-filling book fields from openlibrary APICreate a POST BookListing Route
Create a POST Book Route
Create a 'my profile' page
Create an 'edit profile' formCreate a PATCH UserProfile route
Create a 'my profile' page
Create an 'edit profile' formCreate a PATCH UserProfile route
Add a 'list a new book' nav bar item
Add a 'list new book' action button to the home page
Create a 'create listing' page
Create the 'create listing' form
Create 'create book details' form
Implement pre-filling book fields from openlibrary APICreate a POST BookListing Route
Create a POST Book Route
Create book details page
Create BookReviewList component
Create BookReviewForm componentCreate BookReview JPA entity and repo
Create GET Reviews route under BookController
Create a 'manage books' page to the admin dashboard
Create a link directly to the add book form part of the book listing form
Create a 'manage books' page to the admin dashboard
Add 'edit' links to book cards on the 'manage books' page
Create an edit book details formCreate a PATCH Book route
Create profile details page
Create ProfileReviewList component
Create a profile review formCreate ProfileReview JPA entity and repo
Create UserProfiles Controller
Create GET UserProfileReviews route
Create profile details page
Create ProfileReviewList component
Create a profile review formCreate ProfileReview JPA entity and repo
Create UserProfiles Controller
Create GET UserProfileReviews route
Create 'my orders' page
Create OrderList componentCreate Transaction JPA entity and repo
Create Transactions Controller
Create Transactions GET route
Create 'my orders' page
Create OrderList component
Create 'update status' controlCreate Transaction JPA entity and repo
Create Transactions Controller
Create Transactions GET route
Create Transactions POST update status route
Create 'my orders' page
Create OrderList component
Create 'update status' controlCreate Transaction JPA entity and repo
Create Transactions Controller
Create Transactions GET route
Create Transactions POST update status route
Add a ListingsList component to 'my profile' page that shows this profiles listings
Add a 'remove' button to owned listingsCreate a DELETE BookListing route
Create Book component
Create BookGrid component
Create FilteredBookGrid component
Create books pageCreate Book JPA entity and repo
Create Book controller
Create Filtered GET Book Route
Create Book component
Create BookGrid component
Create FilteredBookGrid component
Create books pageCreate Book JPA entity and repo
Create Book controller
Create Filtered GET Book Route
Create Book component
Create BookGrid component
Create FilteredBookGrid component
Create books pageCreate Book JPA entity and repo
Create Book controller
Create Filtered GET Book Route
Create Book component
Create BookGrid component
Create FilteredBookGrid component
Create books pageCreate Book JPA entity and repo
Create Book controller
Create Filtered GET Book Route

## StoriesForJiraExport
Summary | Description
Story 1 | As an admin user I want to be able to log into Bookaroo so I can access admin level functionality
Story 2 | As a shop owner I want to be able to log into Bookaroo so I can access shop owner level site functionality
Story 3 | As a customer I want to be able to log into Bookaroo so I can access customer site functionality
Story 4 | As an admin user I want to be able to log out of Bookaroo so I can ensure no one accesses my account
Story 5 | As shop owner I want to be able to log out of Bookaroo so I can ensure no one accesses my account
Story 6 | As a customer I want to be able to log out of Bookaroo so I can ensure no one accesses my account
Story 7 | As an unregistered user I want to be able to sign up for a customer account so I am able to log into the application as a customer
Story 8 | As an unregistered shop owner I want to be able to apply for a shop owner account so I can be verified and login as a shop owner
Story 9 | As an admin user I want to be able to approve shop owner account creation requests so I can allow them to log into Bookaroo
Story 10 | As an admin user I want to be able to edit existing accounts so I can ensure account details are up to date
Story 11 | As an admin user I want to be able to suspend existing accounts so I can appropriately moderate the site
Story 12 | As an admin user I want to be able to decline shop owner account creation requests so I can prevent them from logging into Bookaroo
Story 13 | As an admin user I want to be able to view a summary of all transactions on the site sorted by date to verify details of purchases that have been made
Story 14 | As an admin user I want to be able to unsuspend existing accounts so I can appropriately moderate the site
Story 15 | As a customer I want to be able to search for books by their title so I can easily find books listed on the site
Story 16 | As a customer I want to be able to search for books by their author so I can find all books written by a specific author
Story 17 | As a customer I want to be able to search for a book by its ISBN so I can quickly find a book by its unique identifier
Story 18 | As a customer I want to be able to search for books by a specific category so I can find new titles by genres I know I enjoy
Story 19 | As a customer I want to be able to leave a review on a specific book that has been posted to Bookaroo so I can help other users know if the book is worthy of purchase
Story 20 | As a customer I want to be able to view for sale listings for a book that I am interested in so I can compare prices between listings
Story 21 | As a customer I want to be able to complete a purchase of a book via PayPal so I can ensure my payment was done securely
Story 22 | As a customer I want to be able to cancel an order up to 2 hours after I place the order in case so I can change my mind on purchases I make
Story 23 | As a customer I want to be able to request to swap a book I own for a book with another customer so I can get a hold of a book in exchange for one I no longer want
Story 24 | As a customer I want to be able to view a history of my transactions so I can keep track of what I have bought
Story 25 | As a shop owner I want to be able to view the transaction history of my shop so I can track my orders and ensure they are all fufilled
Story 26 | As a customer I want to be able to view more details of a book I find on Bookaroo such as cover image and synopsis so I can decide if I want to purchase a book
Story 27 | As an admin user I want to be able to download a report of all current book listings on the site so I can track what books are currently in stock
Story 28 | As an admin user I want to be able to download a report of all transactions within a given time period so I can track user engagement and site popularity
Story 29 | As a customer I want to be able to view contact details of Bookaroo incase I have issues with the site
Story 30 | As a shop owner I want to be able to view contact details of Bookaroo in case I want to report issues with the site or a customer
Story 31 | As a customer I want to be able to view an "About" page that describes the purpose and history of Bookaroo so I can ensure the site offers the service I require
Story 32 | As a shop owner I want to be able to view an "About" page so I can ensure that Bookaroo offers the service I require
Story 33 | As a shop owner I want to be able to list a used book on Bookaroo so I can allow customers to view and purchase it
Story 34 | As a shop owner I want to be able to list a brand new book on Bookaroo so I can allow customers to view and purchase it
Story 35 | As a customer I want to be able to update/edit my account information so I can make sure the information I provide does not become outdated
Story 36 | As a shop owner I want to be able to update my account details so I can ensure that my details remain up to date
Story 37 | As a customer I want to be able to list a used book for sale so other allow customers to puchase it from me
Story 38 | As a customer I want to be able to share a book listed on Bookaroo so I can show my friends a book I am interested in
Story 39 | As a customer I want to be able to share a listing for a book on Bookaroo so I can show my friends a listing I think is noteworthy
Story 40 | As a customer I want to be able to leave a rating for a book that is listed on Bookaroo so I can provide feedback that other users can view
Story 41 | As an admin user I want to be able to add a book to Bookaroo without needing to create a listing so I can allow customers to see books that may not be in stock
Story 42 | As an admin user I want to be able to edit an existing book on Bookaroo so I can ensure its details are up to date and moderated
Story 43 | As a customer I want to be able to leave a review for a specific shop owner/vendor that I have purchased a book from so I can inform other users of the quality of service
Story 44 | As a customer I want to be able to leave a review on another customers profile so I can help any other customers that may interact with this profile to be aware of the customers service history
Story 45 | As a customer I want to be able to view the current status of my order so I can keep up to date with when I will receive my order
Story 46 | As a shop owner I want to be able to update the status of an order made to me so I can keep the customer up to date with their order
Story 48 | As a customer I want to be able to update the status of a order made for one of the used books I am selling so I can show the buyer the progress of their order
Story 49 | As a shop owner I want to be able to remove a listing I have created on Bookaroo so I can stop customers from purchasing it
Story 50 | As an admin user I want to be able to search for books by its title so I can find a book I want to edit
Story 51 | As a admin user I want to be able to search for books by its author so I can find a book I want to edit
Story 52 | As a admin user I want to be able to search for a book by its ISBN so I can quickly find a book I want to edit
Story 53 | As a admin user I want to be able to search for books by a specific category so I can find a book I want to edit

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #NAME?
| Previous Year | #REF! | #NAME?
| Position | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | As a customer I want to be able to leave a rating for a book that is listed on Bookaroo so I can provide feedback that other users can view | #N/A | #N/A | #N/A | #N/A | #N/A
2 | As an admin user I want to be able to view a summary of all transactions on the site sorted by date to verify details of purchases that have been made | #N/A | #N/A | #N/A | #N/A | #N/A
3 | As a customer I want to be able to complete a purchase of a book via PayPal so I can ensure my payment was done securely | #N/A | #N/A | #N/A | #N/A | #N/A
4 | As a customer I want to be able to cancel an order up to 2 hours after I place the order in case so I can change my mind on purchases I make | #N/A | #N/A | #N/A | #N/A | #N/A
5 | As a customer I want to be able to leave a review for a specific shop owner/vendor that I have purchased a book from so I can inform other users of the quality of service | #N/A | #N/A | #N/A | #N/A | #N/A
6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | As a customer I want to be able to leave a review on another customers profile so I can help any other customers that may interact with this profile to be aware of the customers service history | #N/A | #N/A | #N/A | #N/A | #N/A
9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
15 | As a customer I want to be able to leave a review on a specific book that has been posted to Bookaroo so I can help other users know if the book is worthy of purchase | #N/A | #N/A | #N/A | #N/A | #N/A
16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
17 | As a customer I want to be able to view a history of my transactions so I can keep track of what I have bought | #N/A | #N/A | #N/A | #N/A | #N/A
18 | As a shop owner I want to be able to view the transaction history of my shop so I can track my orders and ensure they are all fulfilled | #N/A | #N/A | #N/A | #N/A | #N/A
19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!